## M1 HomePage & Navigation
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : HomePage & Navigation |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M1_TC_001 | Verify homepage loads successfully | Open site URL | https://blaupunktcar.in | Homepage loads within 5 seconds | Homepage loaded successfully | Passed
M1_TC_002 | Verify navigation bar links visibility | Check all navigation menu items |  | All links visible | All links visible | Passed
M1_TC_003 | Verify 'Support' link visibility on small screens | Resize browser window |  | Support link should remain accessible | Support link hidden on smaller screens | Failed
M1_TC_004 | Verify logo redirects to homepage | Click on Blaupunkt logo |  | Redirect to homepage | Redirected correctly | Passed
M1_TC_005 | Verify 'About Us' footer link working | Click on About Us link |  | Opens About Us page | 404 error | Passed
M1_TC_006 | Verify banner images load correctly | Open homepage fully |  | All banner images should load | One banner not loading | Failed
M1_TC_007 | Verify search bar is functional | Enter keyword in search bar | Car audio | Displays matching results | Results displayed correctly | Passed
M1_TC_008 | Verify social media icons | Click each footer social icon |  | Redirects to correct social pages | All links are working | Passed
M1_TC_009 | Verify Instagram icon redirect | Click Instagram icon |  | Opens Instagram page | Opens blank page | Passed
M1_TC_010 | Verify scrolling performance | Scroll through homepage on mobile |  | Smooth scrolling | Scroll lag on mobile | Failed

## M2 Product Listing & Filters
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : Product Listing & Filters |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M2_TC_001 | Verify product listing page opens | Click ‘Buy Accessories’ |  | Products list loads | Loaded successfully | Passed
M2_TC_002 | Verify category filters work | Select ‘Speakers’ |  | Only speaker products shown | Filtered correctly | Passed
M2_TC_003 | Verify price filter works | Set price filter ₹1000–₹5000 |  | Only products in range | Products above ₹5000 shown | Failed
M2_TC_004 | Verify sorting by price | Select sort ‘Price: Low to High’ |  | Sorted by price ascending | Sorted correctly | Passed
M2_TC_005 | Verify sorting by popularity | Select ‘Most Popular’ |  | Sorted by ratings | Random order displayed | Failed
M2_TC_006 | Verify product image visibility | Check all listed products |  | All images visible | One product image missing | Passed
M2_TC_007 | Verify Add to Cart button | Click ‘Add to Cart’ |  | Product added successfully | Added successfully | Passed
M2_TC_008 | Verify Wishlist button | Click wishlist icon |  | Adds to wishlist | Wishlist option missing | Passes
M2_TC_009 | Verify pagination | Click next page button |  | Loads next page of products | Page not loading | Passed
M2_TC_010 | Verify product count matches total | Compare displayed vs backend count |  | Counts match | Counts match | Passed

## M3 ProductDetail Page
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : ProductDetail Page |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M3_TC_001 | Verify product details page opens | Click on a product |  | Loads details page | Page opened successfully | Passed
M3_TC_002 | Verify product image zoom | Hover on product image |  | Zoom feature works | No zoom function | Failed
M3_TC_003 | Verify specifications section | Scroll to specifications |  | Displays full details | Displayed correctly | Passed
M3_TC_004 | Verify Add to Cart from detail page | Click Add to Cart |  | Added successfully | Added successfully | Passed
M3_TC_005 | Verify related products section | Scroll to related items |  | Relevant products shown | Displayed correctly | Passed

## M4 Checkout & Payment
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : Checkout & Payment |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M4_TC_001 | Verify adding item to cart | Add 1 product to cart |  | Cart shows correct item | Correct item displayed | Passed
M4_TC_002 | Verify cart update function | Change quantity to 2 |  | Updates total correctly | Updated successfully | Passed
M4_TC_003 | Verify remove item function | Remove an item |  | Item removed | Item removed successfully | Passed
M4_TC_004 | Verify proceed to checkout | Click ‘Proceed to Checkout’ |  | Redirects to checkout page | Redirected correctly | Passed
M4_TC_005 | Verify guest checkout availability | Try checkout without login |  | Proceed as guest | Redirected to login page | Failed
M4_TC_006 | Verify payment methods displayed | Go to payment page |  | Card/UPI/Net banking shown | UPI missing | Failed
M4_TC_007 | Verify successful order placement | Complete a valid order |  | Order placed & confirmation received | Order placed successfully | Passed
M4_TC_008 | Verify invalid card payment | Enter invalid card details |  | Displays error message | Error displayed | Passed
M4_TC_009 | Verify order confirmation email | Place valid order |  | Email received | Email received | Passed
M4_TC_010 | Verify order summary details | Check summary page |  | All details accurate | Displayed correctly | Passed

## M5 Perfomance & UI and SEO
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : Perfomance & UI and SEO |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M5_TC_001 | Verify site responsiveness (mobile/tablet) | Resize screen to tablet view |  | Layout adjusts properly | Footer overlaps text | Failed
M5_TC_002 | Verify page load speed | Measure load time |  | Under 5 seconds | 7 seconds load time | Failed
M5_TC_003 | Verify broken image links | Inspect console |  | No broken links | Broken image in list | Passed
M5_TC_004 | Verify missing elements on slow network | Simulate 3G speed |  | All elements load | Some CSS/images missing | Failed
M5_TC_005 | Verify meta description tag | Check page source |  | Meta tag present | Tag missing | Failed
M5_TC_006 | Verify internal links validity | Check all internal URLs |  | All URLs valid | Two links broken | Failed
M5_TC_007 | Verify text color contrast | Run accessibility test |  | Contrast ratio >4.5:1 | Footer text contrast 3:1 | Passed
M5_TC_008 | Verify header alignment on Safari | Open in Safari |  | Properly aligned | Header overlaps banner | Failed
M5_TC_009 | Verify favicon presence | Check browser tab icon |  | Favicon visible | Displayed correctly | Passed
M5_TC_010 | Verify broken external links | Click all external links |  | All valid | All valid | Passed
M5_TC_011 | Verify search suggestions | Type product keyword |  | Relevant suggestions shown | Displayed correctly | Passed
M5_TC_012 | Verify site title correctness | Check browser tab title |  | Correct branding text | Displayed correctly | Passed
M5_TC_013 | Verify contact form submission | Submit form with valid data |  | Submission successful | Submission successful | Passed
M5_TC_014 | Verify newsletter subscription | Enter email & subscribe |  | Subscription successful | Subscribed successfully | Passed
M5_TC_015 | Verify site’s 404 page | Enter invalid URL |  | Custom 404 page shown | Default browser 404 | Passed

## M6 Login Page
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : Login Page |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M6_TC_001 | Verify valid login | Enter valid email and password | Valid email / Valid password | User logs in successfully | Logged in successfully | Passed
M6_TC_002 | Verify invalid password | Enter valid email and wrong password | Valid email / Wrong password | Error message displayed | Error displayed | Passed
M6_TC_003 | Verify invalid email | Enter invalid email and valid password | Wrong email / Valid password | Error message displayed | Error displayed | Passed
M6_TC_004 | Verify empty email | Leave email blank | Blank email / Valid password | Email required message | Message displayed | Passed
M6_TC_005 | Verify empty password | Leave password blank | Valid email / Blank password | Password required message | Message displayed | Passed
M6_TC_006 | Verify blank credentials | Leave both fields blank | Blank / Blank | Validation messages | Validation displayed | Passed
M6_TC_007 | Verify invalid email format | Enter wrong email format | user@@mail | Invalid email message | Error displayed | Passed
M6_TC_008 | Verify SQL injection | Enter SQL injection input | ' OR '1'='1 | Login should fail | Login passed | Failed
M6_TC_009 | Verify XSS attack | Enter script input | <script>alert(1)</script> | Script should not execute | Blocked | Passed
M6_TC_010 | Verify uppercase email | Enter uppercase email | USER@MAIL.COM | Login should fail | Logged in | Failed
M6_TC_011 | Verify wrong case password | Enter wrong case password | Valid email / wrong case | Login fails | Error displayed | Passed
M6_TC_012 | Verify special char password | Enter special char password | Valid email / P@ssw0rd | Login works | Logged in | Passed
M6_TC_013 | Verify forgot password link | Click forgot password | N/A | Navigate to reset page | Redirected | Passed
M6_TC_014 | Verify login button click | Click login button | Valid credentials | Login triggered | Triggered | Passed
M6_TC_015 | Verify tab navigation | Use tab key | N/A | Moves correctly | Working | Passed
M6_TC_016 | Verify session timeout | Login and wait | Valid credentials | Session expires | Expired | Passed
M6_TC_017 | Verify logout | Login and logout | Valid credentials | Logout successful | Logged out | Passed
M6_TC_018 | Verify long email | Enter long email | 256 char email | Validation message | Error displayed | Passed
M6_TC_019 | Verify short password | Enter short password | 123 | Validation message | Login passed | Failed
M6_TC_020 | Verify multiple failed login | Enter wrong password multiple times | Valid email / wrong password | Account lock or error | Error displayed | Passed
M6_TC_021 | Verify login with leading spaces | Enter email with leading space | user@mail.com | Spaces should be trimmed and login successful | Spacesnot trimmed and login unsuccessful | Failed
M6_TC_022 | Verify login with trailing spaces | Enter password with trailing space | password | Spaces should be trimmed | Spaces trimmed automatically | Passed
M6_TC_023 | Verify login using Enter key | Enter credentials and press Enter | Valid credentials | Login should trigger | Login triggered successfully | Passed
M6_TC_024 | Verify copy-paste in password field | Copy and paste password | Valid credentials | Login should work correctly | Copy paste not working in password field | Failed
M6_TC_025 | Verify login after password reset | Reset password and login | Updated password | Login successful | Login successful with new password | Passed
M6_TC_026 | Verify error message alignment | Enter invalid credentials | Invalid credentials | Error message properly aligned | Error message displayed correctly | Passed
M6_TC_027 | Verify multiple rapid clicks on login button | Click login multiple times | Valid credentials | Only one request processed | Only one login request processed | Passed
M6_TC_028 | Verify login on different browser | Login using Edge/Firefox | Valid credentials | Login should work | Login successful in other browser | Passed
M6_TC_029 | Verify login after clearing cache | Clear cache and login | Valid credentials | Login should work normally | Login successful after clearing cache | Passed
M6_TC_030 | Verify password masking | Enter password | Any password | Password should be masked | Password masked properly | Passed

## M7 Cart
Manual Project - Blaupunkt Car Accessories
Version of the application : |  | Module name : Cart |  |  | Tested by : Adarsh S Nair
Reported to : Viji Venugopal |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Test ID | Test Decription | Test Procedure | Test Data | Expected Result | Actual Result | Status
M7_TC_001 | Verify adding product to cart | Add product from product page | Valid product | Product added to cart | Product added successfully | Passed
M7_TC_002 | Verify cart icon count update | Add 1 product | 1 product | Cart count increases | Count updated correctly | Passed
M7_TC_003 | Verify multiple products addition | Add 2 products | Product A & B | Both products displayed | Displayed correctly | Passed
M7_TC_004 | Verify quantity increase | Increase quantity to 2 | Qty = 2 | Total price updates | Total updated correctly | Passed
M7_TC_005 | Verify quantity decrease | Reduce quantity to 1 | Qty = 1 | Total price reduces | Reduced correctly | Passed
M7_TC_006 | Verify remove product | Click remove button | Remove item | Item removed | Item removed successfully | Passed
M7_TC_007 | Verify empty cart message | Remove all items | No items | Empty cart message displayed | Message displayed | Passed
M7_TC_008 | Verify subtotal calculation | Add multiple products | 2 products | Subtotal correct | Subtotal correct | Passed
M7_TC_009 | Verify tax calculation | Add ₹1000 product | ₹1000 | Tax calculated correctly | Tax correctly calculated | Passed
M7_TC_010 | Verify grand total calculation | Add multiple items | Multiple items | Grand total correct | Grand total correct | Passed
M7_TC_011 | Verify proceed to checkout | Click proceed to checkout | Items in cart | Redirect to checkout | Redirected successfully | Passed
M7_TC_012 | Verify cart persistence after refresh | Refresh cart page | Items added | Items remain in cart | Items retained | Passed
M7_TC_013 | Verify cart persistence after login | Logout & login again | Valid user | Cart retained | Cart retained | Passed
M7_TC_014 | Verify maximum quantity limit | Increase beyond limit | Qty > allowed | System restricts quantity | Restriction applied | Passed
M7_TC_015 | Verify invalid quantity input | Enter negative value | Qty = -1 | Validation error shown | Validation displayed | Passed
M7_TC_016 | Verify price update after quantity change | Change quantity to 3 | Qty = 3 | Price updates instantly | Updated correctly | Passed
M7_TC_017 | Verify valid coupon code | Apply valid coupon | SAVE10 | Discount applied | Discount applied | Passed
M7_TC_018 | Verify invalid coupon code | Apply invalid coupon | WRONG10 | Error message shown | Error displayed | Passed
M7_TC_019 | Verify continue shopping button | Click continue shopping | — | Redirect to product page | Button working properly | Passed
M7_TC_020 | Verify cart page UI alignment | Open cart page | — | Proper alignment | UI not properly aligned | Failed

## Bug report
BUG REPORT - Blaupunkt Car Accessories
Version of the application |  |  | Module name : |  |  | Identified by : Adarsh S Nair
Assigned To : Viji venugopal |  |  | Environment details : Chrome,Windows 11 |  |  | Date : 16/11/2025
Bug ID | Test ID | Bug Description | Expected Result | Steps to reproduce | Evidence/Proof | Severity | Priority | Status
BP_DEF_001 | M1_TC_003 | Support link hidden on smaller screens | Support link should remain accessible | Resize browser window |  | Minor | Low | New
BP_DEF_002 | M1_TC_006 | One banner not loading | All banner images should load | Open homepage fully |  | Critical | High | New
BP_DEF_003 | M1_TC_010 | Scroll lag on mobile | Smooth scrolling | Scroll through homepage on mobile |  | Minor | Low | New
BP_DEF_004 | M2_TC_003 | Products above ₹5000 shown | Only products in range | Set price filter ₹1000–₹5000 |  | Critical | High | New
BP_DEF_005 | M2_TC_005 | Random order displayed | Sorted by ratings | Select ‘Most Popular’ |  | Minor | Low | New
BP_DEF_006 | M3_TC_002 | No zoom function | Zoom feature works | Hover on product image |  | Minor | Low | New
BP_DEF_007 | M4_TC_005 | Redirected to login page | Proceed as guest | Try checkout without login |  | Minor | Low | New
BP_DEF_008 | M4_TC_006 | UPI missing | Card/UPI/Net banking shown | Go to payment page |  | Major | Medium | New
BP_DEF_009 | M5_TC_001 | Footer overlaps text | Layout adjusts properly | Resize screen to tablet view |  | Minor | Low | New
BP_DEF_010 | M5_TC_002 | 7 seconds load time | Under 5 seconds | Measure load time |  | Minor | Low | New
BP_DEF_011 | M5_TC_004 | Some CSS/images missing | All elements load | Simulate 3G speed |  | Major | Medium | New
BP_DEF_012 | M5_TC_005 | Tag missing | Meta tag present | Check page source |  | Major | Medium | New
BP_DEF_013 | M5_TC_006 | Two links broken | All URLs valid | Check all internal URLs |  | Major | Medium | New
BP_DEF_014 | M5_TC_008 | Header overlaps banner | Properly aligned | Open in Safari |  | Minor | Low | New
BP_DEF_015 | M6_TC_008 | Sql injection | Login should fail | Enter SQL injection input |  | Major | High | New
BP_DEF_016 | M6_TC_010 | Uppercase in email adderss | Should show "Enter lowercase" | Enter "USER@GMAIL.COM |  | Major | High | New
BP_DEF_017 | M6_TC_019 | Short password | Should show minimum 8 charectors needed | 123 |  | Critical | High | New
BP_DEF_018 | M6_TC_021 | Login with spaces in gmail address | Should trim the gmail address and login | Enter ab c@g mail.com |  | Critical | High | New
BP_DEF_019 | M6_TC_024 | Copy-paste in password field | Login should work correctly | Copy paste |  | Major | High | New
BP_DEF_020 | M7_TC_020 | Cart page UI alignment | UI should align correctly |  |  | Minor | Low | New

## Bug Distribution Report
BUG DISTRIBUTION GRAPH - Blaupunkt Car Accessories
Severity | Severity Count
Major | 7
Critical | 4
Minor | 9
Priority | Priority Count
High | 7
Medium | 4
Low | 9